**South Copeland Community Partnership**

**Outline Delivery Plan 2023/24**

April 2023

| **Activity/ Workstream** | **Delivery Plan** |
| --- | --- |
| **Q1 (Apr – Jun)** | **Q2 (Jul – Sep)** | **Q3 (Oct – Dec)** | **Q4 (Jan – Mar)** |
| **(1)****Communications and Engagement** | * Integrate new communities into South Copeland CP
* Examine the feasibility of a local community engagement hub in South Cumberland
* Conduct Public Opinion Survey
* Refresh website and redesign newsletter
* Commission report on the impact of a GDF for South Cumberland
 | * Feasibility report on a community hub delivered
* Implement a Pilot Community Forum
* Develop arrangements for Annual Community Partnership Report
* Launch refreshed newsletter
 | * Publish Public Opinion Survey results
* Identify lessons learnt from Pilot Community Forum prior to rollout
 | * Publish the Community Impacts Report
* Community Engagement Plan for 2024/5 agreed
* Publish Annual Community Partnership Report
 |
| **(2)****Community Vision** | * Commission review of existing local/regional plans in support of community/economic development
 | * Engage with key stakeholders to agree approach to a community vision
 | * Work with the community to initiate the process to develop a vision
 | * End of year review with a look ahead to 2024
 |
| **(3)****Community Partnership Operations** | * Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2023
* Agree Terms of Reference for subgroups
* Develop and publish Community Partnership Delivery Plan for 2023/4
 | * Review Community Partnership Delivery Plan
 | * Assure the community that key concerns are fully integrated into the developing process for potential Community Withdrawal
 | * Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2024
* Prepare Community Partnership Delivery Plan for 2024/5
 |
| **(4)****Community Investment Funding (CIF)** | * Review Community Investment Panel membership to support implementation of Cumberland Council
 | * Present mid-year performance review
 | * Review Community Investment Funding priorities for 2024
* Review Community Investment Panel membership in readiness for 2024
 | * Present end of year performance review
 |
| **Interface with NWS Activities** | * NWS to present key updates to Community Partnership:
	+ Marine Geophysical Survey
	+ Site evaluation roadmap
	+ Development Consent Order
	+ Property Value Protection scheme
 | * NWS to present key updates to Community Partnership:
	+ Development Consent Order
 | * NWS to present key updates to Community Partnership:
* Priority Site Evaluation study outputs (earliest)
 | * NWS to present key updates to Community Partnership:
* Interpretation of Marine Geophysical Survey data (earliest)
 |