**South Copeland Community Partnership**

**Outline Delivery Plan 2024/25**

April 2024

| **Activity/ Workstream** | **Delivery Plan** | | | |
| --- | --- | --- | --- | --- |
| **Q1 (Apr – Jun)** | **Q2 (Jul – Sep)** | **Q3 (Oct – Dec)** | **Q4 (Jan – Mar)** |
| **(1)**  **Communications and Engagement** | * Development of new CP website * Send introductory letter to open dialogue with neighbouring Parishes and The Lake District National Park as well as Westmorland Council * Publish Public Opinion Survey results from March 2024 * Agree scope of Community Impacts report and understand procurement options | * Begin to understand the seldom heard in the Search Area * Conduct Public Opinion Survey * Development of new CP website * Procure support to carry out Community Impacts Report | * Publish Public Opinion Survey results * Pilot live broadcast of CP meeting * Launch of new CP website (timescales TBC) * Community Forum 1 (Drigg and Millom) * Share draft Community Impacts Report | * Community Engagement Plan for 2025/6 agreed * Publish Annual Community Partnership Report * Identify Lessons learned from CP meeting live broadcast * Community Forum 2 (Drigg and Millom) * Publish final version of Community Impacts Report |
| **(2)**  **Community Vision** | * Understand what the visioning ‘ask’ is * Establish a Visioning Subgroup * Draft Version 0 of a Community Vision – what already exists * Consider different techniques to get community input into Community Vision | * Develop CPs understanding of the Visioning process * Start to get community input into the Vision | * Understand the communities wants & needs to inform the Community Vision * Draft Version 1 of Community Vision | * Publish version 1 of Community Vision * End of year review with a look ahead to 2025 |
| **(3)**  **Community Partnership Operations** | * Publish Community Partnership Delivery Plan for 2024/5 * Publish revised CPA * Publish revised DOIs * Publish CP membership role description and recruitment process * Understand Canadian approach to community withdrawal and Test of Public Support | * Begin to develop withdrawal strategy | * Preparations for recruitment of Chair * Review CP membership in preparation for end of tenure   Mid Year review of Community Partnership Delivery Plan | * Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2025 * Prepare Community Partnership Delivery Plan for 2025/6 * Review Declarations of Interest |
| **(4)**  **Community Investment Funding (CIF)** | * Recruit and Onboard new members of CIF panel | * Present mid-year performance review | * Review Community Investment Funding priorities in preparation for 2025 | * Present end of year performance review * Review Community Investment Panel membership in readiness for 2025 |
| **(5) Other Activities** | * Report back on CP visit to British Geological Survey |  | * Potential visit to Chiltern Tunnels |  |