South Copeland Community Partnership

Outline Delivery Plan 2024/25

April 2024

| Activity/ Workstream | Delivery Plan |  |  |  |
| --- | --- | --- | --- | --- |
|  | Q1 (Apr – Jun) | Q2 (Jul – Sep) | Q3 (Oct – Dec) | Q4 (Jan – Mar) |
| (1) Communications and Engagement | - Development of new CP website - Send introductory letter to open dialogue with neighbouring Parishes and The Lake District National Park as well as Westmorland Council - Publish Public Opinion Survey results from March 2024 - Agree scope of Community Impacts report and understand procurement options | - Begin to understand the seldom heard in the Search Area - Conduct Public Opinion Survey - Development of new CP website - Procure support to carry out Community Impacts Report | - Publish Public Opinion Survey results - Pilot live broadcast of CP meeting - Launch of new CP website (timescales TBC) - Community Forum 1 (Drigg and Millom) - Share draft Community Impacts Report | - Community Engagement Plan for 2025/6 agreed - Publish Annual Community Partnership Report - Identify Lessons learned from CP meeting live broadcast - Community Forum 2 (Drigg and Millom) - Publish final version of Community Impacts Report |
| (2) Community Vision | - Understand what the visioning ‘ask’ is - Establish a Visioning Subgroup - Draft Version 0 of a Community Vision – what already exists - Consider different techniques to get community input into Community Vision | - Develop CPs understanding of the Visioning process - Start to get community input into the Vision | - Understand the communities wants & needs to inform the Community Vision - Draft Version 1 of Community Vision | - Publish version 1 of Community Vision - End of year review with a look ahead to 2025 |
| (3) Community Partnership Operations | - Publish Community Partnership Delivery Plan for 2024/5 - Publish revised CPA - Publish revised DOIs - Publish CP membership role description and recruitment process - Understand Canadian approach to community withdrawal and Test of Public Support | - Begin to develop withdrawal strategy | - Preparations for recruitment of Chair - Review CP membership in preparation for end of tenure Mid Year review of Community Partnership Delivery Plan | - Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2025 - Prepare Community Partnership Delivery Plan for 2025/6 - Review Declarations of Interest |
| (4) Community Investment Funding (CIF) | - Recruit and Onboard new members of CIF panel | - Present mid-year performance review | - Review Community Investment Funding priorities in preparation for 2025 | - Present end of year performance review - Review Community Investment Panel membership in readiness for 2025 |
| (5) Other Activities | - Report back on CP visit to British Geological Survey |  | - Potential visit to Chiltern Tunnels |  |