**South Copeland Community Partnership**

**Outline Delivery Plan 2023/24**

April 2023

| **Activity/ Workstream** | **Delivery Plan** | | | |
| --- | --- | --- | --- | --- |
| **Q1 (Apr – Jun)** | **Q2 (Jul – Sep)** | **Q3 (Oct – Dec)** | **Q4 (Jan – Mar)** |
| **(1)**  **Communications and Engagement** | * Integrate new communities into South Copeland CP * Examine the feasibility of a local community engagement hub in South Cumberland * Conduct Public Opinion Survey * Refresh website and redesign newsletter * Commission report on the impact of a GDF for South Cumberland | * Feasibility report on a community hub delivered * Implement a Pilot Community Forum * Develop arrangements for Annual Community Partnership Report * Launch refreshed newsletter | * Publish Public Opinion Survey results * Identify lessons learnt from Pilot Community Forum prior to rollout | * Publish the Community Impacts Report * Community Engagement Plan for 2024/5 agreed * Publish Annual Community Partnership Report |
| **(2)**  **Community Vision** | * Commission review of existing local/regional plans in support of community/economic development | * Engage with key stakeholders to agree approach to a community vision | * Work with the community to initiate the process to develop a vision | * End of year review with a look ahead to 2024 |
| **(3)**  **Community Partnership Operations** | * Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2023 * Agree Terms of Reference for subgroups * Develop and publish Community Partnership Delivery Plan for 2023/4 | * Review Community Partnership Delivery Plan | * Assure the community that key concerns are fully integrated into the developing process for potential Community Withdrawal | * Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2024 * Prepare Community Partnership Delivery Plan for 2024/5 |
| **(4)**  **Community Investment Funding (CIF)** | * Review Community Investment Panel membership to support implementation of Cumberland Council | * Present mid-year performance review | * Review Community Investment Funding priorities for 2024 * Review Community Investment Panel membership in readiness for 2024 | * Present end of year performance review |
| **Interface with NWS Activities** | * NWS to present key updates to Community Partnership:   + Marine Geophysical Survey   + Site evaluation roadmap   + Development Consent Order   + Property Value Protection scheme | * NWS to present key updates to Community Partnership:   + Development Consent Order | * NWS to present key updates to Community Partnership: * Priority Site Evaluation study outputs (earliest) | * NWS to present key updates to Community Partnership: * Interpretation of Marine Geophysical Survey data (earliest) |