South Copeland Community Partnership

Outline Delivery Plan 2023/24

April 2023

| Activity/ Workstream | Delivery Plan |  |  |  |
| --- | --- | --- | --- | --- |
|  | Q1 (Apr – Jun) | Q2 (Jul – Sep) | Q3 (Oct – Dec) | Q4 (Jan – Mar) |
| (1) Communications and Engagement | - Integrate new communities into South Copeland CP - Examine the feasibility of a local community engagement hub in South Cumberland - Conduct Public Opinion Survey - Refresh website and redesign newsletter - Commission report on the impact of a GDF for South Cumberland | - Feasibility report on a community hub delivered - Implement a Pilot Community Forum - Develop arrangements for Annual Community Partnership Report - Launch refreshed newsletter | - Publish Public Opinion Survey results - Identify lessons learnt from Pilot Community Forum prior to rollout | - Publish the Community Impacts Report - Community Engagement Plan for 2024/5 agreed - Publish Annual Community Partnership Report |
| (2) Community Vision | - Commission review of existing local/regional plans in support of community/economic development | - Engage with key stakeholders to agree approach to a community vision | - Work with the community to initiate the process to develop a vision | - End of year review with a look ahead to 2024 |
| (3) Community Partnership Operations | - Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2023 - Agree Terms of Reference for subgroups - Develop and publish Community Partnership Delivery Plan for 2023/4 | - Review Community Partnership Delivery Plan | - Assure the community that key concerns are fully integrated into the developing process for potential Community Withdrawal | - Review Community Partnership Agreement and Terms of Reference to ensure suitability for 2024 - Prepare Community Partnership Delivery Plan for 2024/5 |
| (4) Community Investment Funding (CIF) | - Review Community Investment Panel membership to support implementation of Cumberland Council | - Present mid-year performance review | - Review Community Investment Funding priorities for 2024 - Review Community Investment Panel membership in readiness for 2024 | - Present end of year performance review |
| Interface with NWS Activities | - NWS to present key updates to Community Partnership: - Marine Geophysical Survey - Site evaluation roadmap - Development Consent Order - Property Value Protection scheme | - NWS to present key updates to Community Partnership: - Development Consent Order | - NWS to present key updates to Community Partnership: - Priority Site Evaluation study outputs (earliest) | - NWS to present key updates to Community Partnership: - Interpretation of Marine Geophysical Survey data (earliest) |